## Task Analysis
Skill Matrix | [8 empty] | Responsibility Matrix
Membro del Team | Project Manager | UX Designer | Frontend Developer | Backend Developer | Database Administrator | DevOps Engineer | QA Tester | IT Acquisition Specialist | Legenda
[9 empty] | R | Responsible: colui che svolge l'attività
Fornitore | [8 empty] | A | Accountable: colui che approva il termine dell'attività
Pietro Magnolia | X | [6 empty] | X | S | Supportive: colui che aiuta il responsabile nello svolgimento dell'attività
Francesco Marroni |  | X | X | [5 empty] | C | Consulted: colui che può consigliare al responsabile
Filippo Ecru |  |  | X |  |  |  | X |  | I | Informed: colui che deve essere tenuto informato sullo stato dell'attività
Federica Viola |  |  |  | X | X
Franca Arancioni |  |  |  | X |  | X |  |  | Id | Task | Risorse Richieste | Magnolia | Marroni | Ecru | Viola | Arancioni | Bordeaux | Kaki | Celeste
Fiorella Bordeaux |  |  | X | [5 empty] | F | Frontend
Fernando Kaki |  |  |  | X |  |  |  |  | F1.1 | Mockup Configuration Page | UX Designer | A | R | I |  |  | I |  | CI
Committente | [8 empty] | F1.2 | Implement Configuration Page | Frontend Developer | I | AC |  |  |  | R |  | I
Paola Celeste | X | [7 empty] | F1.3 | Integrate Configuration Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.4 | Add Public Game option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.5 | Add Private Game option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.6 | Add Friend Game option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.7 | Add No Limit option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.8 | Add Turn Limit option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F1.9 | Add Player Limit option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F2.1 | Mockup Game Participation Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F2.2 | Implement Game Participation Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F2.3 | Integrate Game Participation Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F2.4 | Add Join Public Game option to Frontend | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F2.5 | Add Join Private Game option to Frontend | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F3.1 | Mockup Game Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F3.2 | Implement Game Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F3.3 | Integrate Game Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F3.4 | Show In-Game Messages | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F3.5 | Add In-Game Friend Request option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F4.1 | Mockup Tournament Configuration Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F4.2 | Implement Tournament Configuration Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F4.3 | Integrate Tournament Configuration Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F5.1 | Mockup Tournament Participation Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F5.2 | Implement Tournament Participation Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F5.3 | Integrate Tournament Participation Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F6.1 | Mockup Tournament Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F6.2 | Implement Tournament Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F6.3 | Integrate Tournament Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F7.1 | Mockup Registration Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F7.2 | Implement Registration Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F7.3 | Integrate Registration Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F8.1 | Mockup Login Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F8.2 | Implement Login Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F8.3 | Integrate Login Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F9.1 | Mockup Profile Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F9.2 | Implement Profile Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F9.3 | Integrate Profile Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F10.1 | Mockup Friend Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F10.2 | Implement Friend Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F10.3 | Integrate Friend Page | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F10.4 | Add Friend Request By Username option to Frontend | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F11.1 | Mockup Statistics Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F11.2 | Implement Statistics Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F11.3 | Integrate Statistics Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F12.1 | Mockup Leaderboard Page | UX Designer | A | R | I |  |  | I |  | CI
[9 empty] | F12.2 | Implement Leaderboard Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F12.3 | Integrate Leaderboard Page | Frontend Developer | I | AC | R |  |  |  |  | I
[9 empty] | F13.1 | Show Friend Game Invitation | Frontend Developer | I | RA | [5 empty] | I
[9 empty] | F13.2 | Add Logout option to Frontend | Frontend Developer | I | RA | [5 empty] | I
[9 empty] | F13.3 | Show Friend Chats | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F13.4 | Show Messages | Frontend Developer | I | AC |  |  |  | R |  | I
[9 empty] | F13.5 | Identify Off-The-Shelf Advertisement Solutions | IT Acquisition Specialist | RA | I | I |  |  | I |  | CI
[9 empty] | F13.6 | Integrate Advertisement Solution | Frontend Developer | I | RA | [5 empty] | I
[9 empty] | B | Backend
[9 empty] | B1.1 | Install Tournament Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B1.2 | Design Tournament Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B1.3 | Implement Tournament Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B2.1 | Install Authentication Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B2.2 | Design Authentication Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B2.3 | Implement Authentication Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B3.1 | Install Friend Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B3.2 | Design Friend Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B3.3 | Implement Friend Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B4.1 | Install Chat Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B4.2 | Design Chat Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B4.3 | Implement Chat Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B5.1 | Install Statistics Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B5.2 | Design Statistics Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B5.3 | Implement Score Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B5.4 | Implement Tournament Result Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B6.1 | Install Notification Database | Database Administrator | A |  |  | R | I |  | I | CI
[9 empty] | B6.2 | Design Notification Database | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | B6.3 | Implement Notification Database Queries | Database Administrator | A |  |  | R | I |  | I | I
[9 empty] | A | Authentication Service
[9 empty] | A1.1 | Handle Registration | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A1.2 | Encrypt Sensitive Data | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A1.3 | Send Confirmation Email | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A1.4 | Handle Email Verification | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A2.1 | Handle Token Creation | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A2.2 | Handle Token Expiration | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A2.3 | Handle Token Revocation | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A2.4 | Handle User Permissions | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A3.1 | Get User Profile Information | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | A3.2 | Update User Profile Information | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | S | Statistics Service
[9 empty] | S1.1 | Get Score | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | S1.2 | Get Score History | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | S1.3 | Handle Score Evaluation | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | S2 | Get Ranks | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | N | Notification Service
[9 empty] | N1 | Handle Notification Forwarding | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | G | Game Service
[9 empty] | G1.1 | Model Game Configuration | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.1 | Add Public Game option to Backend | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.2 | Add Private Game option to Backend | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.3 | Handle Friend Invitation | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.4 | Add No Limit option to Backend | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.5 | Add Turn Limit option to Backend | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.1.6 | Add Player Limit option to Backend | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.2 | Initialize Game | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G1.3 | Handle Host Connection | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G2.1 | Handle Public Game Participation | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G2.2 | Handle Private Game Participation | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G2.3 | Handle Friend Game Participation | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G3 | Handle Game Termination | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G4.1 | Analyze Previous Chess Application | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G4.2 | Integrate Previous Chess Application | Backend Developer | A |  |  |  | R |  |  | I
[9 empty] | G5.1 | Get In-Game Messages | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | G5.2 | Handle In-Game Message Sending | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | G5.3 | Handle In-Game Message Receiving | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | G5.4 | Handle In-Game Message Notification | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | T | Tournament Service
[9 empty] | T1.1 | Model Tournament Configuration | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | T1.2 | Initialize Tournament | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | T2.1 | Implement Pairing Algorithm | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | T2.2 | Create Match | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | T2.3 | Notify Match Termination | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | T3 | Handle Tournament Termination | Backend Developer | A |  |  | R | C |  |  | I
[9 empty] | FS | Friend Service
[9 empty] | FS1.1 | Get Friends | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.2 | Get Friend Requests | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.3 | Handle Friend Request Forwarding | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.4 | Handle Accept Friend Request | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.5 | Handle Reject Friend Request | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.6 | Handle Friend Request Notification | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | FS1.7 | Handle Friend Removal | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | M | Message Service
[9 empty] | M1.1 | Get Messages | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | M1.2 | Handle Message Sending | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | M1.3 | Handle Message Forwarding | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | M1.4 | Handle Message Receiving | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | M1.5 | Handle Message Notification | Backend Developer | A |  |  |  | C |  | R | I
[9 empty] | O | Other
[9 empty] | O1 | Integrate Services | DevOps Engineer | A | I | I | I | R | I | I | I
[9 empty] | O2 | Test System | QA Tester | A | I | R | I | I | I | I | I
[9 empty] | O3 | Deploy System | DevOps Engineer | A |  |  |  | R |  |  | CI