## Task Analysis
Costo di Gestione Orario Atteso |  | 19.2
Id | Task | Carico di Lavoro (ore/uomo) | Durata (ore) | Risorse richieste | Stipendi Orari Attesi | Costi di Manodopera | Costi di Strumentazione | Costi di Gestione | Costo Totale Atteso
F | Frontend
F1.1 | Mockup Configuration Page | 9 | 14.9625 | UX Designer | 17.4 | 260.3475 | 0 | 287.28 | 547.6275
F1.2 | Implement Configuration Page | 9.5 | 15.7938 | Frontend Developer | 18 | 284.2875 | 0 | 303.24 | 587.5275
F1.3 | Integrate Configuration Page | 7 | 11.6375 | Frontend Developer | 18 | 209.475 | 0 | 223.44 | 432.915
F1.4 | Add Public Game option to Frontend | 1.25 | 2.0781 | Frontend Developer | 18 | 37.4062 | 0 | 39.9 | 77.3063
F1.5 | Add Private Game option to Frontend | 1.25 | 2.0781 | Frontend Developer | 18 | 37.4062 | 0 | 39.9 | 77.3063
F1.6 | Add Friend Game option to Frontend | 1.5 | 2.4938 | Frontend Developer | 18 | 44.8875 | 0 | 47.88 | 92.7675
F1.7 | Add No Limit option to Frontend | 1.25 | 2.0781 | Frontend Developer | 18 | 37.4062 | 0 | 39.9 | 77.3063
F1.8 | Add Turn Limit option to Frontend | 1.25 | 2.0781 | Frontend Developer | 18 | 37.4062 | 0 | 39.9 | 77.3063
F1.9 | Add Player Limit option to Frontend | 1.25 | 2.0781 | Frontend Developer | 18 | 37.4062 | 0 | 39.9 | 77.3063
F2.1 | Mockup Game Participation Page | 7 | 11.6375 | UX Designer | 17.4 | 202.4925 | 0 | 223.44 | 425.9325
F2.2 | Implement Game Participation Page | 9 | 14.9625 | Frontend Developer | 18 | 269.325 | 0 | 287.28 | 556.605
F2.3 | Integrate Game Participation Page | 9 | 14.9625 | Frontend Developer | 18 | 269.325 | 0 | 287.28 | 556.605
F2.4 | Add Join Public Game option to Frontend | 2 | 3.325 | Frontend Developer | 18 | 59.85 | 0 | 63.84 | 123.69
F2.5 | Add Join Private Game option to Frontend | 2 | 3.325 | Frontend Developer | 18 | 59.85 | 0 | 63.84 | 123.69
F3.1 | Mockup Game Page | 9.5 | 15.7938 | UX Designer | 17.4 | 274.8112 | 0 | 303.24 | 578.0512
F3.2 | Implement Game Page | 14.5 | 24.1063 | Frontend Developer | 18 | 433.9125 | 0 | 462.84 | 896.7525
F3.3 | Integrate Game Page | 6 | 9.975 | Frontend Developer | 18 | 179.55 | 0 | 191.52 | 371.07
F3.4 | Show In-Game Messages | 4 | 6.65 | Frontend Developer | 18 | 119.7 | 0 | 127.68 | 247.38
F3.5 | Add In-Game Friend Request option to Frontend | 4 | 6.65 | Frontend Developer | 18 | 119.7 | 0 | 127.68 | 247.38
F4.1 | Mockup Tournament Configuration Page | 10 | 16.625 | UX Designer | 17.4 | 289.275 | 0 | 319.2 | 608.475
F4.2 | Implement Tournament Configuration Page | 9 | 14.9625 | Frontend Developer | 18 | 269.325 | 0 | 287.28 | 556.605
F4.3 | Integrate Tournament Configuration Page | 7.5 | 12.4688 | Frontend Developer | 18 | 224.4375 | 0 | 239.4 | 463.8375
F5.1 | Mockup Tournament Participation Page | 8.5 | 14.1313 | UX Designer | 17.4 | 245.8837 | 0 | 271.32 | 517.2038
F5.2 | Implement Tournament Participation Page | 8 | 13.3 | Frontend Developer | 18 | 239.4 | 0 | 255.36 | 494.76
F5.3 | Integrate Tournament Participation Page | 10 | 16.625 | Frontend Developer | 18 | 299.25 | 0 | 319.2 | 618.45
F6.1 | Mockup Tournament Page | 16 | 26.6 | UX Designer | 17.4 | 462.84 | 0 | 510.72 | 973.56
F6.2 | Implement Tournament Page | 18 | 29.925 | Frontend Developer | 18 | 538.65 | 0 | 574.56 | 1113.21
F6.3 | Integrate Tournament Page | 8 | 13.3 | Frontend Developer | 18 | 239.4 | 0 | 255.36 | 494.76
F7.1 | Mockup Registration Page | 9 | 14.9625 | UX Designer | 17.4 | 260.3475 | 0 | 287.28 | 547.6275
F7.2 | Implement Registration Page | 10 | 16.625 | Frontend Developer | 18 | 299.25 | 0 | 319.2 | 618.45
F7.3 | Integrate Registration Page | 4.5 | 7.4813 | Frontend Developer | 18 | 134.6625 | 0 | 143.64 | 278.3025
F8.1 | Mockup Login Page | 6 | 9.975 | UX Designer | 17.4 | 173.565 | 0 | 191.52 | 365.085
F8.2 | Implement Login Page | 7.5 | 12.4688 | Frontend Developer | 18 | 224.4375 | 0 | 239.4 | 463.8375
F8.3 | Integrate Login Page | 7 | 11.6375 | Frontend Developer | 18 | 209.475 | 0 | 223.44 | 432.915
F9.1 | Mockup Profile Page | 9 | 14.9625 | UX Designer | 17.4 | 260.3475 | 0 | 287.28 | 547.6275
F9.2 | Implement Profile Page | 16.5 | 27.4313 | Frontend Developer | 18 | 493.7625 | 0 | 526.68 | 1020.4425
F9.3 | Integrate Profile Page | 10.5 | 17.4563 | Frontend Developer | 18 | 314.2125 | 0 | 335.16 | 649.3725
F10.1 | Mockup Friend Page | 10.5 | 17.4563 | UX Designer | 17.4 | 303.7387 | 0 | 335.16 | 638.8988
F10.2 | Implement Friend Page | 20 | 33.25 | Frontend Developer | 18 | 598.5 | 0 | 638.4 | 1236.9
F10.3 | Integrate Friend Page | 13.5 | 22.4438 | Frontend Developer | 18 | 403.9875 | 0 | 430.92 | 834.9075
F10.4 | Add Friend Request By Username option to Frontend | 4.5 | 7.4813 | Frontend Developer | 18 | 134.6625 | 0 | 143.64 | 278.3025
F11.1 | Mockup Statistics Page | 15.5 | 25.7688 | UX Designer | 17.4 | 448.3762 | 0 | 494.76 | 943.1363
F11.2 | Implement Statistics Page | 24 | 39.9 | Frontend Developer | 18 | 718.2 | 0 | 766.08 | 1484.28
F11.3 | Integrate Statistics Page | 9 | 14.9625 | Frontend Developer | 18 | 269.325 | 0 | 287.28 | 556.605
F12.1 | Mockup Leaderboard Page | 17 | 28.2625 | UX Designer | 17.4 | 491.7675 | 0 | 542.64 | 1034.4075
F12.2 | Implement Leaderboard Page | 15.5 | 25.7688 | Frontend Developer | 18 | 463.8375 | 0 | 494.76 | 958.5975
F12.3 | Integrate Leaderboard Page | 12.5 | 20.7812 | Frontend Developer | 18 | 374.0625 | 0 | 399 | 773.0625
F13.1 | Show Friend Game Invitation | 15 | 24.9375 | Frontend Developer | 17.4 | 433.9125 | 0 | 478.8 | 912.7125
F13.2 | Add Logout option to Frontend | 2.5 | 4.1562 | Frontend Developer | 18 | 74.8125 | 0 | 79.8 | 154.6125
F13.3 | Show Friend Chats | 7.5 | 12.4688 | Frontend Developer | 18 | 224.4375 | 0 | 239.4 | 463.8375
F13.4 | Show Messages | 6 | 9.975 | Frontend Developer | 18 | 179.55 | 0 | 191.52 | 371.07
F13.5 | Identify Off-The-Shelf Advertisement Solutions | 72.5 | 120.5312 | IT Acquisition Specialist | 17.2 | 2073.1375 | 20000 | 2314.2 | 24387.3375
F13.6 | Integrate Advertisement Solution | 21.25 | 35.3281 | Frontend Developer | 18 | 635.9062 | 0 | 678.3 | 1314.2062
B | Backend
B1.1 | Install Tournament Database | 21.5 | 35.7437 | Database Administrator | 18.5 | 661.2594 | 2200 | 686.28 | 3547.5394
B1.2 | Design Tournament Database | 18.5 | 30.7563 | Database Administrator | 18.5 | 568.9906 | 0 | 590.52 | 1159.5106
B1.3 | Implement Tournament Database Queries | 20.5 | 34.0813 | Database Administrator | 18.5 | 630.5031 | 0 | 654.36 | 1284.8631
B2.1 | Install Authentication Database | 21.5 | 35.7437 | Database Administrator | 18.5 | 661.2594 | 2200 | 686.28 | 3547.5394
B2.2 | Design Authentication Database | 20.5 | 34.0813 | Database Administrator | 18.5 | 630.5031 | 0 | 654.36 | 1284.8631
B2.3 | Implement Authentication Database Queries | 22 | 36.575 | Database Administrator | 18.5 | 676.6375 | 0 | 702.24 | 1378.8775
B3.1 | Install Friend Database | 21.5 | 35.7437 | Database Administrator | 18.5 | 661.2594 | 2200 | 686.28 | 3547.5394
B3.2 | Design Friend Database | 18.5 | 30.7563 | Database Administrator | 18.5 | 568.9906 | 0 | 590.52 | 1159.5106
B3.3 | Implement Friend Database Queries | 15.5 | 25.7688 | Database Administrator | 18.5 | 476.7219 | 0 | 494.76 | 971.4819
B4.1 | Install Chat Database | 21.5 | 35.7437 | Database Administrator | 18.5 | 661.2594 | 2200 | 686.28 | 3547.5394
B4.2 | Design Chat Database | 18.5 | 30.7563 | Database Administrator | 18.5 | 568.9906 | 0 | 590.52 | 1159.5106
B4.3 | Implement Chat Database Queries | 18.5 | 30.7563 | Database Administrator | 18.5 | 568.9906 | 0 | 590.52 | 1159.5106
B5.1 | Install Statistics Database | 20.5 | 34.0813 | Database Administrator | 18.5 | 630.5031 | 2200 | 654.36 | 3484.8631
B5.2 | Design Statistics Database | 23 | 38.2375 | Database Administrator | 18.5 | 707.3938 | 0 | 734.16 | 1441.5538
B5.3 | Implement Score Database Queries | 12.5 | 20.7812 | Database Administrator | 18.5 | 384.4531 | 0 | 399 | 783.4531
B5.4 | Implement Tournament Result Database Queries | 12 | 19.95 | Database Administrator | 18.5 | 369.075 | 0 | 383.04 | 752.115
B6.1 | Install Notification Database | 21 | 34.9125 | Database Administrator | 18.5 | 645.8813 | 2200 | 670.32 | 3516.2013
B6.2 | Design Notification Database | 16.5 | 27.4313 | Database Administrator | 18.5 | 507.4781 | 0 | 526.68 | 1034.1581
B6.3 | Implement Notification Database Queries | 12 | 19.95 | Database Administrator | 18.5 | 369.075 | 0 | 383.04 | 752.115
A | Authentication Service
A1.1 | Handle Registration | 11.5 | 19.1188 | Backend Developer | 19.6 | 374.7275 | 0 | 367.08 | 741.8075
A1.2 | Encrypt Sensitive Data | 10 | 16.625 | Backend Developer | 19.6 | 325.85 | 0 | 319.2 | 645.05
A1.3 | Send Confirmation Email | 4.5 | 7.4813 | Backend Developer | 19.6 | 146.6325 | 0 | 143.64 | 290.2725
A1.4 | Handle Email Verification | 8 | 13.3 | Backend Developer | 19.6 | 260.68 | 0 | 255.36 | 516.04
A2.1 | Handle Token Creation | 10 | 16.625 | Backend Developer | 19.6 | 325.85 | 0 | 319.2 | 645.05
A2.2 | Handle Token Expiration | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
A2.3 | Handle Token Revocation | 4.5 | 7.4813 | Backend Developer | 19.6 | 146.6325 | 0 | 143.64 | 290.2725
A2.4 | Handle User Permissions | 18 | 29.925 | Backend Developer | 19.6 | 586.53 | 0 | 574.56 | 1161.09
A4.1 | Get User Profile Information | 14 | 23.275 | Backend Developer | 19.6 | 456.19 | 0 | 446.88 | 903.07
A4.2 | Update User Profile Information | 6.5 | 10.8063 | Backend Developer | 19.6 | 211.8025 | 0 | 207.48 | 419.2825
S | Statistics Service
S1.1 | Get Score | 7 | 11.6375 | Backend Developer | 19.6 | 228.095 | 0 | 223.44 | 451.535
S1.2 | Get Score History | 4.5 | 7.4813 | Backend Developer | 19.6 | 146.6325 | 0 | 143.64 | 290.2725
S1.3 | Handle Score Evaluation | 7.5 | 12.4688 | Backend Developer | 19.6 | 244.3875 | 0 | 239.4 | 483.7875
S2 | Get Ranks | 6 | 9.975 | Backend Developer | 19.6 | 195.51 | 0 | 191.52 | 387.03
N | Notification Service
N1 | Handle Notification Forwarding | 15 | 24.9375 | Backend Developer | 19.6 | 488.775 | 0 | 478.8 | 967.575
G | Game Service
G1.1 | Model Game Configuration | 21.5 | 35.7437 | Backend Developer | 19.6 | 700.5775 | 0 | 686.28 | 1386.8575
G1.1.1 | Add Public Game option to Backend | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
G1.1.2 | Add Private Game option to Backend | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
G1.1.3 | Handle Friend Invitation | 8.5 | 14.1313 | Backend Developer | 19.6 | 276.9725 | 0 | 271.32 | 548.2925
G1.1.4 | Add No Limit option to Backend | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
G1.1.5 | Add Turn Limit option to Backend | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
G1.1.6 | Add Player Limit option to Backend | 3 | 4.9875 | Backend Developer | 19.6 | 97.755 | 0 | 95.76 | 193.515
G1.2 | Initialize Game | 9.5 | 15.7938 | Backend Developer | 19.6 | 309.5575 | 0 | 303.24 | 612.7975
G1.3 | Handle Host Connection | 8.5 | 14.1313 | Backend Developer | 19.6 | 276.9725 | 0 | 271.32 | 548.2925
G2.1 | Handle Public Game Participation | 19.5 | 32.4188 | Backend Developer | 19.6 | 635.4075 | 0 | 622.44 | 1257.8475
G2.2 | Handle Private Game Participation | 22.5 | 37.4062 | Backend Developer | 19.6 | 733.1625 | 0 | 718.2 | 1451.3625
G2.3 | Handle Friend Game Participation | 26 | 43.225 | Backend Developer | 19.6 | 847.21 | 0 | 829.92 | 1677.13
G3 | Handle Game Termination | 18 | 29.925 | Backend Developer | 19.6 | 586.53 | 0 | 574.56 | 1161.09
G4.1 | Analyze Previous Chess Application | 84 | 139.65 | Backend Developer | 19.6 | 2737.14 | 0 | 2681.28 | 5418.42
G4.2 | Integrate Previous Chess Application | 74 | 123.025 | Backend Developer | 19.6 | 2411.29 | 0 | 2362.08 | 4773.37
G5.1 | Get In-Game Messages | 10.5 | 17.4563 | Backend Developer | 19.6 | 342.1425 | 0 | 335.16 | 677.3025
G5.2 | Handle In-Game Message Sending | 15.5 | 25.7688 | Backend Developer | 19.6 | 505.0675 | 0 | 494.76 | 999.8275
G5.3 | Handle In-Game Message Receiving | 12 | 19.95 | Backend Developer | 19.6 | 391.02 | 0 | 383.04 | 774.06
G5.4 | Handle In-Game Message Notification | 11 | 18.2875 | Backend Developer | 19.6 | 358.435 | 0 | 351.12 | 709.555
T | Tournament Service
T1.1 | Model Tournament Configuration | 19 | 31.5875 | Backend Developer | 19.6 | 619.115 | 0 | 606.48 | 1225.595
T1.2 | Initialize Tournament | 11 | 18.2875 | Backend Developer | 19.6 | 358.435 | 0 | 351.12 | 709.555
T2.1 | Implement Pairing Algorithm | 18 | 29.925 | Backend Developer | 19.6 | 586.53 | 0 | 574.56 | 1161.09
T2.2 | Create Match | 12 | 19.95 | Backend Developer | 19.6 | 391.02 | 0 | 383.04 | 774.06
T2.3 | Notify Match Termination | 9 | 14.9625 | Backend Developer | 19.6 | 293.265 | 0 | 287.28 | 580.545
T3 | Handle Tournament Termination | 19 | 31.5875 | Backend Developer | 19.6 | 619.115 | 0 | 606.48 | 1225.595
FS | Friend Service
FS1.1 | Get Friends | 5.5 | 9.1438 | Backend Developer | 19.6 | 179.2175 | 0 | 175.56 | 354.7775
FS1.2 | Get Friend Requests | 4.5 | 7.4813 | Backend Developer | 19.6 | 146.6325 | 0 | 143.64 | 290.2725
FS1.3 | Handle Friend Request Forwarding | 17 | 28.2625 | Backend Developer | 19.6 | 553.945 | 0 | 542.64 | 1096.585
FS1.4 | Handle Accept Friend Request | 8.5 | 14.1313 | Backend Developer | 19.6 | 276.9725 | 0 | 271.32 | 548.2925
FS1.5 | Handle Reject Friend Request | 5 | 8.3125 | Backend Developer | 19.6 | 162.925 | 0 | 159.6 | 322.525
FS1.6 | Handle Friend Request Notification | 7 | 11.6375 | Backend Developer | 19.6 | 228.095 | 0 | 223.44 | 451.535
FS1.7 | Handle Friend Removal | 8.5 | 14.1313 | Backend Developer | 19.6 | 276.9725 | 0 | 271.32 | 548.2925
M | Message Service
M1.1 | Get Messages | 7.5 | 12.4688 | Backend Developer | 19.6 | 244.3875 | 0 | 239.4 | 483.7875
M1.2 | Handle Message Sending | 13 | 21.6125 | Backend Developer | 19.6 | 423.605 | 0 | 414.96 | 838.565
M1.3 | Handle Message Forwarding | 10.5 | 17.4563 | Backend Developer | 19.6 | 342.1425 | 0 | 335.16 | 677.3025
M1.4 | Handle Message Receiving | 11 | 18.2875 | Backend Developer | 19.6 | 358.435 | 0 | 351.12 | 709.555
M1.5 | Handle Message Notification | 9 | 14.9625 | Backend Developer | 19.6 | 293.265 | 0 | 287.28 | 580.545
O | Other
O1 | Integrate Services | 107.5 | 178.7188 | DevOps Engineer | 21.79 | 3894.2816 | 0 | 3431.4 | 7325.6816
O2 | Test System | 57.5 | 95.5938 | QA Tester | 18 | 1720.6875 | 0 | 1835.4 | 3556.0875
O3 | Deploy System | 38 | 63.175 | DevOps Engineer | 21.79 | 1376.5833 | 17600 | 1212.96 | 20189.5432
Totale |  | 1782 | 2962.575 |  | 2377.68 | 56112.4423 | 50800 | 56881.44 | 163793.8823