## Task Analysis
Service Work Packages |  | Project Work Packages |  | Team Work Packages
Id | Task | Id | Task | Id | Task
Frontend Work Package |  | Critical Work Package |  | Magnolia Work Package
F1.1 | Mockup Configuration Page | F3.3 | Integrate Game Page | F13.5 | Identify Off-The-Shelf Advertisement Solutions
F1.2 | Implement Configuration Page | B1.1 | Install Tournament Database | Marroni Work Package
F1.3 | Integrate Configuration Page | B1.2 | Design Tournament Database | F1.1 | Mockup Configuration Page
F1.4 | Add Public Game option to Frontend | B1.3 | Implement Tournament Database Queries | F2.1 | Mockup Game Participation Page
F1.5 | Add Private Game option to Frontend | B2.1 | Install Authentication Database | F3.1 | Mockup Game Page
F1.6 | Add Friend Game option to Frontend | B2.2 | Design Authentication Database | F4.1 | Mockup Tournament Configuration Page
F1.7 | Add No Limit option to Frontend | B2.3 | Implement Authentication Database Queries | F5.1 | Mockup Tournament Participation Page
F1.8 | Add Turn Limit option to Frontend | B3.1 | Install Friend Database | F6.1 | Mockup Tournament Page
F1.9 | Add Player Limit option to Frontend | B3.2 | Design Friend Database | F7.1 | Mockup Registration Page
|  | B3.3 | Implement Friend Database Queries | F8.1 | Mockup Login Page
F2.1 | Mockup Game Participation Page | B5.1 | Install Statistics Database | F9.1 | Mockup Profile Page
F2.2 | Implement Game Participation Page | B5.2 | Design Statistics Database | F10.1 | Mockup Friend Page
F2.3 | Integrate Game Participation Page | B5.3 | Implement Score Database Queries | F11.1 | Mockup Statistics Page
F2.4 | Add Join Public Game option to Frontend | B5.4 | Implement Tournament Result Database Queries | F12.1 | Mockup Leaderboard Page
F2.5 | Add Join Private Game option to Frontend | B6.1 | Install Notification Database | F13.1 | Show Friend Game Invitation
|  | B6.2 | Design Notification Database | F13.2 | Add Logout option to Frontend
F3.1 | Mockup Game Page | B6.3 | Implement Notification Database Queries | F13.6 | Integrate Advertisement Solution
F3.2 | Implement Game Page | S1.1 | Get Score | Ecru Work Package
F3.3 | Integrate Game Page | S1.2 | Get Score History | F2.2 | Implement Game Participation Page
F3.4 | Show In-Game Messages | S1.3 | Handle Score Evaluation | F2.3 | Integrate Game Participation Page
F3.5 | Add In-Game Friend Request option to Frontend | S2 | Get Ranks | F2.4 | Add Join Public Game option to Frontend
|  | G5.1 | Get In-Game Messages | F2.5 | Add Join Private Game option to Frontend
F4.1 | Mockup Tournament Configuration Page | G5.2 | Handle In-Game Message Sending | F5.2 | Implement Tournament Participation Page
F4.2 | Implement Tournament Configuration Page | G5.3 | Handle In-Game Message Receiving | F5.3 | Integrate Tournament Participation Page
F4.3 | Integrate Tournament Configuration Page | G5.4 | Handle In-Game Message Notification | F7.2 | Implement Registration Page
|  | FS1.1 | Get Friends | F7.3 | Integrate Registration Page
F5.1 | Mockup Tournament Participation Page | FS1.2 | Get Friend Requests | F9.2 | Implement Profile Page
F5.2 | Implement Tournament Participation Page | FS1.3 | Handle Friend Request Forwarding | F9.3 | Integrate Profile Page
F5.3 | Integrate Tournament Participation Page | FS1.4 | Handle Accept Friend Request | F11.2 | Implement Statistics Page
|  | FS1.5 | Handle Reject Friend Request | F11.3 | Integrate Statistics Page
F6.1 | Mockup Tournament Page | FS1.6 | Handle Friend Request Notification | F12.2 | Implement Leaderboard Page
F6.2 | Implement Tournament Page | FS1.7 | Handle Friend Removal | F12.3 | Integrate Leaderboard Page
F6.3 | Integrate Tournament Page | M1.1 | Get Messages | O2 | Test System
|  | M1.2 | Handle Message Sending | Viola Work Package
F7.1 | Mockup Registration Page | M1.3 | Handle Message Forwarding | B1.1 | Install Tournament Database
F7.2 | Implement Registration Page | M1.4 | Handle Message Receiving | B1.2 | Design Tournament Database
F7.3 | Integrate Registration Page | M1.5 | Handle Message Notification | B1.3 | Implement Tournament Database Queries
|  | O1 | Integrate Services | B2.1 | Install Authentication Database
F8.1 | Mockup Login Page | O2 | Test System | B2.2 | Design Authentication Database
F8.2 | Implement Login Page | O3 | Deploy System | B2.3 | Implement Authentication Database Queries
F8.3 | Integrate Login Page | Closing Work Package |  | B3.1 | Install Friend Database
|  | O1 | Integrate Services | B3.2 | Design Friend Database
F9.1 | Mockup Profile Page | O2 | Test System | B3.3 | Implement Friend Database Queries
F9.2 | Implement Profile Page | O3 | Deploy System | B4.1 | Install Chat Database
F9.3 | Integrate Profile Page |  |  | B4.2 | Design Chat Database
|  |  |  | B4.3 | Implement Chat Database Queries
F10.1 | Mockup Friend Page |  |  | B5.1 | Install Statistics Database
F10.2 | Implement Friend Page |  |  | B5.2 | Design Statistics Database
F10.3 | Integrate Friend Page |  |  | B5.3 | Implement Score Database Queries
F10.4 | Add Friend Request By Username option to Frontend |  |  | B5.4 | Implement Tournament Result Database Queries
|  |  |  | B6.1 | Install Notification Database
F11.1 | Mockup Statistics Page |  |  | B6.2 | Design Notification Database
F11.2 | Implement Statistics Page |  |  | B6.3 | Implement Notification Database Queries
F11.3 | Integrate Statistics Page |  |  | T1.1 | Model Tournament Configuration
|  |  |  | T1.2 | Initialize Tournament
F12.1 | Mockup Leaderboard Page |  |  | T2.1 | Implement Pairing Algorithm
F12.2 | Implement Leaderboard Page |  |  | T2.2 | Create Match
F12.3 | Integrate Leaderboard Page |  |  | T2.3 | Notify Match Termination
|  |  |  | T3 | Handle Tournament Termination
F13.1 | Show Friend Game Invitation |  |  | Arancioni Work Package
F13.2 | Add Logout option to Frontend |  |  | G1.1 | Model Game Configuration
F13.3 | Show Friend Chats |  |  | G1.1.1 | Add Public Game option to Backend
F13.4 | Show Messages |  |  | G1.1.2 | Add Private Game option to Backend
F13.5 | Identify Off-The-Shelf Advertisement Solutions |  |  | G1.1.3 | Handle Friend Invitation
F13.6 | Integrate Advertisement Solution |  |  | G1.1.4 | Add No Limit option to Backend
Backend Work Package |  |  |  | G1.1.5 | Add Turn Limit option to Backend
B1.1 | Install Tournament Database |  |  | G1.1.6 | Add Player Limit option to Backend
B1.2 | Design Tournament Database |  |  | G1.2 | Initialize Game
B1.3 | Implement Tournament Database Queries |  |  | G1.3 | Handle Host Connection
|  |  |  | G2.1 | Handle Public Game Participation
B2.1 | Install Authentication Database |  |  | G2.2 | Handle Private Game Participation
B2.2 | Design Authentication Database |  |  | G2.3 | Handle Friend Game Participation
B2.3 | Implement Authentication Database Queries |  |  | G3 | Handle Game Termination
|  |  |  | G4.1 | Analyze Previous Chess Application
B3.1 | Install Friend Database |  |  | G4.2 | Integrate Previous Chess Application
B3.2 | Design Friend Database |  |  | O1 | Integrate Services
B3.3 | Implement Friend Database Queries |  |  | O3 | Deploy System
Bordeaux Work Package
B4.1 | Install Chat Database |  |  | F1.2 | Implement Configuration Page
B4.2 | Design Chat Database |  |  | F1.3 | Integrate Configuration Page
B4.3 | Implement Chat Database Queries |  |  | F1.4 | Add Public Game option to Frontend
|  |  |  | F1.5 | Add Private Game option to Frontend
B5.1 | Install Statistics Database |  |  | F1.6 | Add Friend Game option to Frontend
B5.2 | Design Statistics Database |  |  | F1.7 | Add No Limit option to Frontend
B5.3 | Implement Score Database Queries |  |  | F1.8 | Add Turn Limit option to Frontend
B5.4 | Implement Tournament Result Database Queries |  |  | F1.9 | Add Player Limit option to Frontend
|  |  |  | F3.2 | Implement Game Page
B6.1 | Install Notification Database |  |  | F3.3 | Integrate Game Page
B6.2 | Design Notification Database |  |  | F3.4 | Show In-Game Messages
B6.3 | Implement Notification Database Queries |  |  | F3.5 | Add In-Game Friend Request option to Frontend
Authentication Work Package |  |  |  | F4.2 | Implement Tournament Configuration Page
A1.1 | Handle Registration |  |  | F4.3 | Integrate Tournament Configuration Page
A1.2 | Encrypt Sensitive Data |  |  | F6.2 | Implement Tournament Page
A1.3 | Send Confirmation Email |  |  | F6.3 | Integrate Tournament Page
A1.4 | Handle Email Verification |  |  | F8.2 | Implement Login Page
|  |  |  | F8.3 | Integrate Login Page
A2.1 | Handle Token Creation |  |  | F10.2 | Implement Friend Page
A2.2 | Handle Token Expiration |  |  | F10.3 | Integrate Friend Page
A2.3 | Handle Token Revocation |  |  | F10.4 | Add Friend Request By Username option to Frontend
A2.4 | Handle User Permissions |  |  | F13.3 | Show Friend Chats
|  |  |  | F13.4 | Show Messages
A3.1 | Get User Profile Information |  |  | Kaki Work Package
A3.2 | Update User Profile Information |  |  | A1.1 | Handle Registration
Statistics Work Package |  |  |  | A1.2 | Encrypt Sensitive Data
S1.1 | Get Score |  |  | A1.3 | Send Confirmation Email
S1.2 | Get Score History |  |  | A1.4 | Handle Email Verification
S1.3 | Handle Score Evaluation |  |  | A2.1 | Handle Token Creation
|  |  |  | A2.2 | Handle Token Expiration
S2 | Get Ranks |  |  | A2.3 | Handle Token Revocation
Notification Work Package |  |  |  | A2.4 | Handle User Permissions
N1 | Handle Notification Forwarding |  |  | A3.1 | Get User Profile Information
Game Work Package |  |  |  | A3.2 | Update User Profile Information
G1.1 | Model Game Configuration |  |  | S1.1 | Get Score
G1.1.1 | Add Public Game option to Backend |  |  | S1.2 | Get Score History
G1.1.2 | Add Private Game option to Backend |  |  | S1.3 | Handle Score Evaluation
G1.1.3 | Handle Friend Invitation |  |  | S2 | Get Ranks
G1.1.4 | Add No Limit option to Backend |  |  | N1 | Handle Notification Forwarding
G1.1.5 | Add Turn Limit option to Backend |  |  | G5.1 | Get In-Game Messages
G1.1.6 | Add Player Limit option to Backend |  |  | G5.2 | Handle In-Game Message Sending
G1.2 | Initialize Game |  |  | G5.3 | Handle In-Game Message Receiving
G1.3 | Handle Host Connection |  |  | G5.4 | Handle In-Game Message Notification
|  |  |  | FS1.1 | Get Friends
G2.1 | Handle Public Game Participation |  |  | FS1.2 | Get Friend Requests
G2.2 | Handle Private Game Participation |  |  | FS1.3 | Handle Friend Request Forwarding
G2.3 | Handle Friend Game Participation |  |  | FS1.4 | Handle Accept Friend Request
|  |  |  | FS1.5 | Handle Reject Friend Request
G3 | Handle Game Termination |  |  | FS1.6 | Handle Friend Request Notification
|  |  |  | FS1.7 | Handle Friend Removal
G4.1 | Analyze Previous Chess Application |  |  | M1.1 | Get Messages
G4.2 | Integrate Previous Chess Application |  |  | M1.2 | Handle Message Sending
|  |  |  | M1.3 | Handle Message Forwarding
G5.1 | Get In-Game Messages |  |  | M1.4 | Handle Message Receiving
G5.2 | Handle In-Game Message Sending |  |  | M1.5 | Handle Message Notification
G5.3 | Handle In-Game Message Receiving
G5.4 | Handle In-Game Message Notification
Tournament Work Package
T1.1 | Model Tournament Configuration
T1.2 | Initialize Tournament
T2.1 | Implement Pairing Algorithm
T2.2 | Create Match
T2.3 | Notify Match Termination
T3 | Handle Tournament Termination
Friend Work Package
FS1.1 | Get Friends
FS1.2 | Get Friend Requests
FS1.3 | Handle Friend Request Forwarding
FS1.4 | Handle Accept Friend Request
FS1.5 | Handle Reject Friend Request
FS1.6 | Handle Friend Request Notification
FS1.7 | Handle Friend Removal
Message Work Package
M1.1 | Get Messages
M1.2 | Handle Message Sending
M1.3 | Handle Message Forwarding
M1.4 | Handle Message Receiving
M1.5 | Handle Message Notification